## Sheet1
Task | Sub-task | Duration(working days)
Database
| Schema | 3
| Implementation of schema | 5
| Security | 2
Web Application
| Creating forms for add, update and delete for relevant users | 12
| Search utility | 4
| Viewing items | 3
2D/3D images with texts
Video and 3D modeling upon request
Virtual tour
| Multiple Virtual discussion rooms | 10
Martketing |  | 3
SEO