## Sheet1
Task | Sub-task | Duration(Working hours)
Implementation of Color Scheme |  | 10
| Navigation | 2
| Heading and Paragraph | 2
| Other details on all pages | 6
Implementation of Fonts and Font sizes |  | 10
| Navigation | 2
| Heading and Paragraph | 2
| Other details on all pages | 6
Setting up Home page with new Design |  | 8
Testing and comparison with designs |  | 7
| Total | 35