## Sheet1
Date | Day | Duration(hours) | Comment
2020-06-15 | Monday
|  | 1 | Identify Email Tracking problem
2020-06-16 | Tuesday
|  | 2 | fixed Mailbox issue to resolve it
2020-07-09 | Thursday
|  | 5 | Microsft CRM Email Tracking
2020-07-10 | Friday
|  | 2 | Change Request
2020-07-13 | Monday
|  | 2 | Ticket No.
2020-07-14 | Tuesday
|  | 7.5 | Support Queue
2020-07-27 | Monday
|  | 1 | Identify Email Tracking problem
2020-07-28 | Tuesday
|  | 2 | Worked on fixing the issue
2020-07-29 | Wednesday
|  | 2 | Identifying the problem and tried to resolve issue by setting encoding(didn't work)
2020-07-30 | Thursday
|  | 1 | R & D to resolve the issue and posted on Community
2020-07-31 | Friday
|  | 2 | R & D to resolve the issue. Community suggested to open ticket on Microsoft. Sent details on how to open tixket to Julio.
2020-08-11 | Tuesday
|  | 1 | Identify Email Tracking problem |  | Quoted hours | Actual hours
|  | 1 | identify activities duplicate issue | Email tracking | 2 | 5
2020-08-12 | Wednesday |  |  | activity duplicate issue | 8 | 6
|  | 1 | looked for logs and found main problem for email tracking
|  | 1 | isolated duplicated activities and had discussion with Julio on findings
2020-08-13 | Thursday
|  | 0.5 | Julio mentioned tracking issue is realted to login and we agreed for sharing screen
2020-08-17 | Monday
|  | 1 | Worked on the duplicate activities issue and found a queue of user
2020-08-18 | Tuesday
|  | 1 | Julio sent screenshot of login error. We tried to identify it and found it is from ADFS
|  | 2 | Compared duplicate queues and found that they were not duplicate and forward email activities had dates of the activity date or one day prior date
2020-08-19 | Wednesday
|  | 1 | Screen shared with user of Gabriel with login issue. It was found that she tried to login 3-4 times in 10 seconds or 17 second(too many logins). Mentioned it to Julio and started to look for work around
|  | 1 | Made sure that activity issue is not an issue on basis of previous day finiding and told Julio
2020-08-21 | Friday
|  | 0.5 | Sent steps for to fix login issue to julio.
2020-08-24 | Monday
|  | 1 | Performed those steps myself to fix issue on user's machine(didn't fixed)
2020-08-26 | Wednesday
Suggested to change browser to Firefox. Chrome don’t support trusted sites(issue was chrome specific)
2020-08-28 | Friday
|  | 4 | Julio updated CRM SSL certificates and everthing fell apart. Worked with Kishore(SpruceTech) to fix the issue
|  | 2 | Outlook login issue started again for all users(login page has http 404 not found error)
| Total(hours) | 45.5